ARK Implementation Checklist

Text = Red text denotes core tasks to be completed.

| Phase 1 : Preparation [from decision to join ARK programme] | ( | Additional notes |
| --- | --- | --- |
| I have completed the ARK online tool |  |  |
| I have reviewed the resources website |  |  |
| I have signed up to the ARK Champions’ Network |  |  |
| I have attended at least one ARK Champions’ Network meeting / teleconference |  |  |
| I have outlined the flow of acute general medical patients in my hospital |  |  |
| I have listed the existing processes for antibiotic prescribing and stewardship |  |  |
| I have identified the local barriers to effective ‘review and revise’ |  |  |
| I have identified strategies to overcome the local barriers |  |  |
| I have identified a method for recording in the drug chart the Decision Aid categories |  |  |
| I have reviewed the trust’s ‘review and revise’ audit data |  |  |
| I have identified how I will monitor the impact of ARK |  |  |
| I have obtained the board level support required |  |  |
| I have investigated how to get the ARK online tool included in the Trust’s learning and development programme |  |  |
| I have investigated how to get the ARK online tool included in the appraisal process |  |  |
| I have identified and recruited the staff to involve in the ARK Core Team |  |  |

| Phase 2: Planning and Piloting [4 months before implementation] | ( | Additional notes |
| --- | --- | --- |
| I have sent the links to the online tool and resources website to the ARK Core Team members (before the initial planning meeting) |  |  |
| I have held an initial planning meeting with the ARK Core Team |  |  |
| During the meeting, I have introduced the aims of the ARK implementation |  |  |
| I have discussed the Decision Aid and how to use it in local practice |  |  |
| I have reviewed data available on ‘review and revise’ in my Trust |  |  |
| I have discussed the main barriers and developed strategies (please send your completed barriers and solutions template to orh-tr.ark-hospital@nhs.net) |  |  |
| I have discussed how ARK will be launched and established |  |  |
| I have planned the organisation of the kick off meetings for the wider clinical team |  |  |
| I have discussed how we will gather data to assess the adoption and impact of the intervention |  |  |
| I have discussed how to facilitate regular, supportive discussion with the wider clinical team regarding the implementation of ARK |  |  |
| I have discussed how ARK will be sustained |  |  |
| We have agreed on the specific roles of the team members |  |  |
| I have arranged for ongoing ARK Core Team meetings |  |  |
| I have piloted the local implementation tools / processes |  |  |
| I have the approval to integrate the Decision Aid into the existing prescription system |  |  |
| I have approval to use the patient leaflet |  |  |
| I have obtained learning and development approval for the ARK online tool |  |  |

| Phase 3: Organise kick-off [2 months before implementation] | ( | Additional notes |
| --- | --- | --- |
| I have made a list of people to involve in the wider clinical team |  |  |
| I have identified 20-30 key members of staff who would be actively engaged and willing to help implement ARK |  |  |
| I have made a list of other people who might be interested |  |  |
| I have organised and publicised the kick-off meetings |  |  |

| Phase 4: Get Ready for Implementation [2 weeks before implementation] | ( | Additional notes |
| --- | --- | --- |
| I have reminded staff to complete the online tool before the kick-off meetings |  |  |
| I have sent a second reminder to staff to complete the online tool just before the kick off meetings |  |  |
| I have run the kick-off meetings |  |  |
| During the meeting I have presented the national and local rationale to ARK (including the presentation of local audit data) |  |  |
| I have made sure everyone had completed the ARK online tool |  |  |
| I have discussed with the staff how to use the Decision Aid in local practice |  |  |
| I have explained how ARK will use data collection and feedback |  |  |
| I have discussed potential barriers and addressed the team’s concerns |  |  |
| I have organised regular discussion meetings with clinical teams to monitor performance and rates of antibiotic prescribing |  |  |
| I have organised regular ward rounds and huddles to monitor staff awareness and use of the decision aid |  |  |

| Phase 5: Implementation [0 weeks] | ( | Additional notes |
| --- | --- | --- |
| I have started the implementation from the planned implementation date |  |  |

| Phase 6: Ongoing Implementation | ( | Additional notes |
| --- | --- | --- |
| I have collected objective evidence on how ARK is being implemented |  |  |
| I have examined how current rates compare to baseline and the ARK and CQUIN targets |  |  |
| I have sent anonymised copies of the data collection tool to the research team at orh-tr.ark-hospital@nhs.net |  |  |
| I have provided regular, supportive feedback to the wider clinical team (based on the data collected) |  |  |
| I have explored with the wider clinical team how the decision aid is being used in practice and identified and addressed any barriers |  |  |
| I have discussed case examples taken from recent daily practice with the wider clinical team to stimulate discussion on how to implement the decision aid |  |  |
| I have held regular meetings with the ARK Core Team |  |  |
| I have ensured new staff train in ARK |  |  |
| I have provided adequate handover in the event of staff changeover |  |  |
| I have planned for ongoing data collection |  |  |
| I have planned for ongoing discussion with the wider clinical team |  |  |

Please send a copy of the completed checklist to the ARK research team at orh-tr.ark-hospital@nhs.net.